## Defect Summary
Defect Summary Report
Total Number of Bugs | Test cases executed | Closed Bugs | Deffered Bugs | Reopened | To Do | In progress /Under development | QA Verification
4 | 65 | 0 | 0 | 0 | 4 | 0 | 0

## Defect Report
Demo Web Shop - Bug Report
Bug ID | Test case Id | Bug Title | Bug Description | Step to Reproduce | Test Data | Expected Result | Actual Result | Priority | Severity | Visual proof | Issue Type | Envionment | Platform | Device | Assignee | Status | Comments | Verified By
DEF_01 | SS_13 | Invalid email format | No warning message is displayed and was able to register with invalid email format | 1. Navigate to url 2. Click Sign in 3. Click Register your account 4. Fill the registration form with an invalid email id | Email: abhi.com@gmail.com | "E-mail format is invalid" warning message should be displayed | No warning message is displayed and was able to register with invalid email format | High | High |  | Bug | Staging | Windows 11 | Lenovo | Developer | Open |  | Abhinesh M S
DEF_02 | CP_08 | File format specification | No error or warning message is displayed | 1. Navigate to url 2. Click Contact link 3. Fill the form 4. Attach jpg file 5. Click Send |  | Error message or warning message should be displayed on uploading a file in different format | No error or warning message is displayed | High | High |  | Bug | Staging | Windows 11 | Lenovo | Developer | Open |  | Abhinesh M S
DEF_03 | CO_08 | Masked credit card input and CVV protection | CVV and card details are exposed in plain text and not masked | 1. Navigate to url 2. Click a product card 3. Click "Add to cart" button 4. Click cart icon at the top 5. Click proceed to check out till we reach step 3 6. Enter the details 7. Click proceed to check out 8. Click on the "Choose your payment method" drop down 9. Select Credit card 10. Enter card details |  | CVV input characters should be masked and full card credentials should not exposed | CVV and card details are exposed in plain text and not masked | High | Critical |  | Bug | Staging | Windows 11 | Lenovo | Developer | Open |  | Abhinesh M S
DEF_04 | CO_10 | Quantity Controls | Application allows to complete the transaction and no error message is displayed when the quantity is set to zero | 1. Add an item to cart 2. Click cart icon 3. Set quantity to 0 in step 1 4. Click proceed to check out |  | User must not be able to complete the transaction when the quantity is set to zero | Application allows to complete the transaction and no error message is displayed when the quantity is set to zero | High | Critical |  | Bug | Staging | Windows 11 | Lenovo | Developer | Open |  | Abhinesh M S